## Checker Screen
Tester Name: Muhammad Ali |  | URL: https://consistly.ai/
Website Name: Consistly.ai |  | Execution Date: 19-07-2026
Module | Remarks | Checkbox
Signup | New account creation, continue with google or linkedin, manual add details for creating an account, redirect to on boarding. | TRUE
Signin | Login with valid/invalid credentials, error handling and redirect to dashboard. | TRUE
Forget Password/ Reset | Reset link request, email delivery, reset form, and login with new password. | TRUE
Dashboard/Home | LinkedIn account linking, AI-based post generation, post scheduling and publishing. | TRUE
Recommendations | Suggests 3 targeted posts to comment on, aimed to boosting reach and engagement on your posts. | TRUE
Ideas | Weekly AI- based post ideas based on your strategy and skills | TRUE
Hooks | Creates first 2 opening lines for a given topic(Insight story, Sharp take, Structured insight,Behind the build), so the user can pick the strongest hook to lead a LinkedIn post. | TRUE
Carousels | Converts a post into a multi-slide visual carousel. Free plan gets 'Standard Template' 'Pro Template' is locked behind Upgrade. | TRUE
Calendar | Shows all your published, scheduled and draft posts with dates. | TRUE
Activity | Tracks all of your post, see recent content, and monitors your consistency. | TRUE
Insights | Shows performance and analytics from users activity and engagement on the post. | TRUE
Engage | Suggests linkedin people profiles to engage with based on the users content pillars includes keywords and location search. | TRUE
Job | Search LinkedIn job openings and save the ones worth following up on. View Profile links and Add to favourites too. | TRUE
Strategy | Shows the content strategy that drives AI generative ideas, pillars, themes, rules and current plan as a summary card. Edit strategy option to update summary. | TRUE
Feedback | Send feedback directly to the Consistly team and share your feedback to improve. | TRUE

## Checklist
Tester Name: | Muhammad Ali |  | Execution Date: 21-07-2026
Website Name: | Consistly.ai
Test Scenario | Expected Result | Status | Remarks | Suggestions
Signup
Verify that the Sign Up page loads correctly when the "Get Started" button in the navigation bar is clicked. | The Sign Up page should load successfully when the user clicks the 'Get Started' button in the navigation bar. | PASS | Working Fine
Verify Full name field validation. | Field should be required and empty field should display an error message. | PASS | Working Fine
Verify email field format validation. | Only valid email format should be accepted and otherwise it should display an error. | PASS | Working Fine
Verify duplicate email handling. | Signing up with an email that already has an account should shows a clear 'account already exists' message. | PASS | Working Fine
Verify password field minimum strength/length rules. | Password below the minimum length should be rejected with a clear rule explanation shown to the user. | PASS | Working Fine
Verify empty form submission. | Submitting with all fields empty should show validation errors on every required field, not just the first. | PASS | Working Fine
Verify signup with browser autofill password manager. | Autofill email and password should populate correctly and pass validation. | PASS | Working Fine
Verify Terms and conditions / Privacy Policy checkbox. | Form should not submit until the checkbox is checked. | PASS | Working Fine
Verify Sign Up with Google. | Clicking 'Sign up with Google' should open the Google account picker, and a successful selection should create a Consistly account using the Google email and redirect to dashboard. | PASS | Working Fine
Verify Sign Up with LinkedIn. | Clicking 'Sign up with LinkedIn' should open LinkedIn's OAuth consent screen, and a successful authorization should create a Consistly account using the LinkedIn profile picture and redirect to dashboard. | PASS | Working Fine
Verify Sign Up with mobile view. | All fields, labels, and the submit button should remain usable and fully visible. | PASS | Working Fine
Sign In
Verify that the Sign In page loads correctly when the "SignIn" button in the navigation bar is clicked. | The Signin page should load successfully when the user clicks the 'Sign In' button in the navigation bar. | PASS | Working Fine
Verify login with valid, correct credentials. | User should redirect to the dashboard. | PASS | Working Fine
Verify login with incorrect password. | Invalid email and password' error message should display. | PASS | Working Fine
Verify login with empty fields. | Both fields should display an error message and login button should be disabled. | PASS | Working Fine
Verify Sign In with google. | Clicking 'Sign in with Google' should authenticate an existing Google linked account and land on the dashboard. | PASS | Working Fine
Verify Sing In with LinkedIn | Clicking 'Sign in with LinkedIn' should authenticate an existing LinkedIn linked account and land on the dashboard. | PASS | Working Fine
Verify Sign In page with mobile view. | All fields, labels, and the submit button should remain usable and fully visible. | PASS | Working Fine
Forget Password
Verify forget password link is clickable and working properly. | Link should open the password reset request form. | PASS | Working Fine
Verify reset request with a valid registered email. | A reset email should be sent and a confirmation message should display on screen. | PASS | Working Fine
Verify setting a new password via the reset form. | New password should follow the same strength rules as signup and successfully update the account. | PASS | Working Fine
Verify login with the new password after reset. | User should be able to log in immediately using the newly set password. | PASS | Working Fine
Dashboard- LinkedIn Account linking
Verify 'Connect LinkedIn' option is visible on the dashboard for a not yet linked account. | Option shoud be visible and prompt the user to connect their linkedIn account. | PASS | Working Fine
Verify connecting a LinkedIn account via OAuth. | User should be redirected to LinkedIns consent screen, and on approval, the account should show as linked account in dashboard. | PASS | Working Fine
Verify dashboard reflects the connected LinkedIn account's name. | LinkedIn identity should display correctly once connected. | PASS | Working Fine
Verify posting and scheduling is blocked until LinkedIn is linked. | Attempting to schedule,publish before linking LinkedIn should prompt the user to connect first. | PASS | Working Fine
Verify disconnecting the LinkedIn account. | User should be able to disconnect LinkedIn profile from settings. | PASS | Working Fine
Dashboard- Home/ Overview
Verify Homepage loads correctly after login. | Page should load with greetings and shows all the elements of the page correctly. | PASS | Working Fine
Verify greeting message displays correctly. | Greeting should show correct time based message with your accurate name which is linked. | PASS | Working Fine
Verify voice training banner. | Banner should show step indicator and option to add 2-3 voice sample | PASS | Working Fine
Verify 'Your next Move' recommendation pannel. | Pannel should show the track of your LinkedIn post.
Verify Logo button works | Clicking on logo should redirect to main home page of consistly.ai | PASS | Working FIne
Dashboard- Create
Verify ideas section working properly. | Generate ideas and should upload on your linked LinkedIn account. | PASS | Working Fine
Verify weekly content ideas generate based on onboarding inputs. | User can generate AI-based post to share on LinkedIn and add | PASS | Working Fine
Verify word limits on idea generated box. | User should write at least 3 min words of topic to create an AI generated post. | PASS | Working Fine
Verify plan based limits on ideas per week are enforced. | User should generate only one post per week if he is using starter pack | PASS | Working Fine
Verify Hooks page loads and work properly. | Page should load with topic fiel, mode selection and 'Generate 5 hooks' button visible. | PASS | Working Fine
Verify topic field validation on empty submission. | It shouldnot allow empty field validation, 'Generate 5 hooks' button should disabled. | PASS | Working Fine
Verify all four mod options are selectable. | Clicking on any mode should highlight and only one mode should be selected at a time. | PASS | Working Fine
Verify generated hooks are relevant to the entered topic. | All 5 hooks should be relevant to the entered topic. | PASS | Working Fine
Verify default selected mode on page load. | Insight Story' should be pre selected by default. | PASS | Working Fine
Verify switching mode after hooks are generated regenerates new hooks. | Changing mode and clicking generate again should produce 5 new hooks in new style. | PASS | Working Fine
Verify Saved tab functionality | Saved' tab should show previously saved hooks. | PASS | Working Fine
Verify Carousels page loads correctly from slidebar. | Page should load with title, description, template options. | PASS | Working Fine
Verify 'Use Standard Template' option. | User should pick a design and customize text to create a carousels. | PASS | Working Fine
Verify 'Use Pro Template' option is locked for free plan. | Pro template' should appear disabled and not be clickable for free users. | PASS | Working Fine
Verify creating a carousel from a topic/prompt. | User should be able to enter a topic and system shoud generate slides based on the topic. | PASS | Working Fine
Verify the changing font, colors of carousels. | User should have options to change the font, size and color of pages. | PASS | Working Fine
Verify the changing of number of slides to 2 pages. | User should have option to change the number of slides to 1 or 2. | FAIL | Not Working
Manage - Calender
Verify calender page loads correctly from slidebar. | Calender should open on the current month with today's date. | PASS | Working Fine
Verify Months navigation. | Clicking on '<' and '>' should move the calender back and forward correctly. | PASS | Working Fine
Verify status dots on dates. | Dates with post should show a colored dot matching the correct action. | PASS | Working Fine
Verify clicking a post card edits that post. | Clicking a post in the list should open its full content for viewing or editing. | PASS | Working Fine
Verify autosave feature. | Any edit in a post should autosave instantly. | FAIL | Not Working
Verify save button. | Save button should save that edited item. | PASS | Working Fine
Verify 'Refine Your Post' box. | User should be able to refine AI generated post by predefined feature or add custom changes. | PASS | Working Fine
Verify a Published post cannot be rescheduled. | Published posts should be read only. | PASS | Working Fine
Verify clicking buttons under 'All Posts'. | Button should be clickable and work according to their features. | PASS | Working Fine
Manage - Activity
Verify Activity page loads correctly from slidebar. | Page should load with title, description, 4 stats cards. | PASS | Working Fine
Verify 'Posts' stat card count accuracy. | Number shown in card should match the actual number of posts. | PASS | Working Fine
Verify 'Carousels' stat card count accuracy. | Number shown in card should match the actual number of carousels. | PASS | Working Fine
Verify 'Engagements' stat card count accuracy. | Number shown in card should match the actual number of comments on a post. | PASS | Working Fine
Verify 'This Month' stat card count accuracy. | Number shown should reflect only activity from the curent calender. | PASS | Working Fine
Verify stat card updates after new activity or post. | Creating and publishing new post should add the accurate number in stat card. | PASS | Working Fine
Manage - Insights
Verify Insights page loads correctly from slidebar. | Page should load with title, description, 4 stat cards, performance section, and audience and content with no broken elements. | PASS | Working Fine
Verify 'Posts.7 Days' stat card accuracy. | Count should match actual posts published in last 7 days with correct label. | PASS | Working Fine
Verify "Avg Engagement' stat card behaviour with no data. | System should show 'Post more to unlock' until user posts more content. | PASS | Working Fine
Verify 'Target .30D' stat card behaviour with no data. | System should show 'Add engagement targets' user to set targets | PASS | Working Fine
Verify 'Pillar Balance' stat card accuraccy. | System should show accurate ratio and label should based on how many pillars have been used in content. | PASS | Working Fine
Verify 'Performance' section once enough data exists. | Should display an actual content performance by posting day, format and style. | Blocked | Not tested
Verify 'Audience and Intent' section displays target audience text. | Should correctly shows the audience description set during onboarding. | PASS | Working Fine
Verify 'Scheduling Queue' behaviour. | Should displays the posts which are already scheduled and going live in next 7 days. | Blocked | Not tested
Share Feedbacks
Verify feedback page loads correctly from slidebar. | Clicking it should open 'How's Consistly working for you?' popup over screen. | PASS | Working Fine
Verify star rating selection. | Clicking a star should highlight that many stars, and rating should be recorded correctly. | PASS | Working Fine
Verify feedback text box accepts input. | User should be able to type feedback text into the box. | PASS | Working Fine
Verify 'Send feedback' button state with no rating selected. | Button should remain disabled until at least a rating is given. | PASS | Working Fine
Verify 'Send feedback' button becomes active after selecting a rating. | Button should become enabled once a star rating is selected. | PASS | Working Fine
Verify 'Cancel' button closes the modal without submitting. | Clicking 'Cancel' should close the popup and discard any entered feedback. | PASS | Working Fine

## Test Cases
Tester Name: | Muhammad Ali
Website Name: | Consistly.ai
ID | Title | Test Scenario | Pre-conditions | Steps to Reproduce | Expected Result | Actual Result | Status
TC_01 | Signup-valid credential | Verify a user can signup with valid credentials. | User is on the consistly home page. | 1.Click on 'get started' top right corner of navbar. 2.Open signup page. 3.Enter a valid full name, unique email and a password meeting strength rules. 4.Check the Terms checkbox. 5.CLick signup. | Account is created and user is redirected to onboarding Step 1. | As expected | PASS
TC_02 | Signup-Invalid email format | Verify signup block an invalid format or give an error. | User is on signup page. | 1.Enter irregular email format. 2.Fill all remaining fields correctly. 3.Click signup. | Form should block submission and shows an error of 'Invalid email'. | As expected | PASS
TC_03 | Signup with duplicate mail | Verify signup blocks an email that already has an account. | User is on signup page. | 1. Enter the existing account's email. 2.Fill remaining fields correctly. 3.Click Signup. | Form should show 'account already exists' error and not create a duplicate account on same email. | As expected | PASS
TC_04 | Sign Up with weak password | Verify signup blocks a password below the minimum strength. | User is on the signup page. | 1.Enter a short simple password otherthan their rules. 2.Fill remaining fields corrrectly. 3.Click signup. | Form should disabled the create or signup button and displays the password rules. | As expected | PASS
TC_05 | Sign Up with Google | Verify a new user can successfuly signup with google. | User is on signup page and has google account. | 1.Click on continue with google. 2.Select google account in popup. 3.Check email and confirm account. | Account should be created using the Google email and user is redirected to onboarding Step 1. | As expected | PASS
TC_06 | Sign Up with LinkedIn | Verify a new user can sign up successfully using LinkedIn. | User is on the signup page and has a LinkedIn account. | 1.Click on continue with LinkedIn. 2.LinkedIn Sign In page popsup. 3.Enter LinkedIn credential and confirm. | Account should be created using the LinkedIn email and user is redirected to onboarding Step 1. | As expected | PASS
TC_07 | Sign In with valid credentials | Verify an existing user can log in with correct credentials. | User has already registered account, | 1.Click on 'Sign In' top right corner of navbar. 2.Enter correct email and password. 3.Click SignIn. | User should redirected to dashboard. | As expected | PASS
TC_08 | Sign In with incorrect password. | Verify login is blocked with an incorrect password. | User has already registered account. | 1.Click on 'Sign In' top right corner of navbar. 2.Enter correct email and incorrect password. 3.Click SignIn. | Sytem should display an error of 'Email and password is incorrect' error. | As expected | PASS
TC_09 | Sign In with unregistered email | Verify login is blocked with an incorrect password. | User is on login page. | 1. Enter an unregistered email with any password. 2. Click Sign In. | Error should display that email doesnot exist. | As expected | PASS
TC_10 | Sign In with Google | Verify an existing user can log in using Google. | User previously SignedUp google account. | 1. Click 'Continue with Google' on the login page. 2. Select the linked Google account. | User is redirected to the dashboard. | As expected | PASS
TC_11 | Sign In with LinkedIn | Verify an existing user can log in using LinkedIn. | User previously SignedUp LinkedIn account. | 1.Click on continue with LinkedIn. 2.LinkedIn Sign In page popsup. 3.Enter LinkedIn credential and confirm. | User is redirected to the dashboard. | As expected | PASS
TC_12 | Forgot Password with valid email | Verify a password reset email is sent for a registered account. | User is on login page. User has registered account. | 1.Click 'Forgot password' on the login page. 2.Enter the registered email and submit. 3.Check email and click on the link. 4.Enter new password and confirm. | A reset email is sent and a confirmation message is shown on screen. | As expected | PASS
TC_13 | Logo Navigation | Verify logo click returns user to homepage. | User is on any page. | Click the logo in the top left of the header. | User is redirected to the dashboard. | As expected | PASS
TC_14 | On boarding page loads. | Verify the onboarding page behaviour. | User has just completed SignUp or SignIn. | 1. Complete SignUp/SignIn. 2. Observe the page that loads next. | Tell us about you' screen appears with progress bar at 0% and 'About 3 minutes' estimate shown. | As expected | PASS
TC_15 | Progress Bar Accuracy | Verify the progress bar accuracy working. | User is onboarding page. | 1. Complete Step 1 and move to Step 2. 2. Observe the progress bar. | Progress bar percentage should increase to reflect completed steps. | As expected | PASS
TC_16 | Predefined Option selection | Verify clicking on predefined option selection. | User is on the 'Tell us about you' page with an empty textbox. | 1. Click on any predefined option. 2. Observe the textbox content. | Textbox auto-fills with example background text relevant to their option, | As expected | PASS
TC_17 | Manual text entry | Verify user to enter manual text. | User is on the 'Tell us about you' page. | 1. Click into the textbox. 2. Type a custom background description. | Text should enter freely and override any previously prefilled content. | As expected | PASS
TC_18 | Empty fields | Verify onboarding page with empty box. |  | 1. Leave the textbox empty. 2. Click 'Next'. | Next' button remains disabled and page does not proceed to Step 2 | As expected | PASS
TC_19 | On boarding next steps. | Verify the next steps of onboarding. | User is onboarding page. | 1. Fill in goal, audience, content pillars. 2. Paste a voice sample. 3. Click Next. | After filling all the steps system should generate a post according to their filled data. | As expected | PASS
TC_20 | Sign Out Session | Verify Signout clears the session. | User is logged in. | 1. Click SignOut. 2. Attempt to navigate back to the dashboard URL directly. | User is logged out and redirected to login when revisiting the dashboard URL. | As expected | PASS
TC_21 | Home-Greeting and Week Overview | Verify the Home dashboard greets the user and shows weekly status. | User has logged in and completed onboarding. | Land on the dashboard page after login | Personalized greeting (correct name/time of day) and 'All caught up' or pending ideas status should display correctly. | As expected | PASS
TC_22 | Home — Generate Ideas Button | Verify generating a fresh batch of ideas from Home. | User has worked through all current ideas. | 1. Click 'Generate ideas' on the Home page. | A new batch of content ideas should generate without error. | As expected | PASS
TC_23 | Home — Recommendations Filter | Verify the 'Your Next Move' recommendations filter tabs. | User is on the dashboard page with recommendations present. | 1. Click through All, Engage, Performance, Cadence, and Pillars filter tabs. | Each tab should show only recommendations of that category, with counts matching the tab labels. | As expected | PASS
TC_24 | Hooks — Generate 5 Hooks | Verify generating hooks for a topic and mode. | User is on the Hooks page. | 1. Enter a topic in the Topic field. 2. Select any mode. 3. Click 'Generate 5 hooks'. | 5 hooks should generate, matching the topic and selected mode's tone. | As expected | PASS
TC_25 | Hooks — Empty Topic Validation | Verify hook generation button is disabled without topic. | User is on the Hooks page with empty topic field. | 1. Leave Topic field empty. 2. Click 'Generate 5 hooks'. | Error should display that no action taken without any topic. | Disabled Hook button. | Fail
TC_26 | Hooks — Save & View Saved Hooks | Verify saving a hook and viewing it in the Saved tab. | User has generated at least one hook. | 1. Save a generated hook. 2. Click the 'Saved' tab. | The saved hook should appear correctly in the Saved tab | As expected | PASS
TC_27 | Carousels — Create from Standard Template | Verify creating a carousel using the Standard Template | User is on the Carousels page. | 1. Click 'Use Standard Template'. 2. Pick a design and customize the text. 3. Save the carousel. | A carousel should be created and appear in the Carousels list, replacing the 'No carousels yet' empty state. | As expected | PASS
TC_28 | Carousels — Pro Template | Verify the Pro Template is accessible on the Free plan. | User is on the Carousels page. | 1.Click on 'Use Pro Template' | Pro template should display and user should select from them. | Pro template button is disabled due to the use of free plan. | Fail
TC_29 | Calendar — View Current Month | Verify the Calendar loads on the current month with today highlighted. | User navigates the calender from slidebar. | 1.Open the calender. | Current month should display with today's date visibly highlighted. | As expected | PASS
TC_30 | Calendar — Status Accuracy | Verify calendar date dots match the Published/Scheduled/Draft. | User has at least one post in status. | 1. Observe the dots on dated cells against the calendar. | Dot colors on each date should correctly correspond to the post's actual status. | As expected | PASS
TC_31 | Activity — Stat Card accuracy | Verify Posts, Carousels, Engagements and This Month stat cards. | User has some activity history. | 1. Open the Activity page. 2. Compare each stat card to the users actual activity. | Each stat card count should accurately reflect real activity data. | As expected | PASS
TC_32 | Activity — Feed Item Detail | Verify an activity page item shows correct type, status, and pillar tags. | User has at least one published post. | 1. Open the Activity page. 2. Check the most recent activity item. | Item should show the correct content type, status and pillar tag. | As expected | PASS
TC_33 | Insights — Stat Cards with Insufficient Data | Verify Avg Engagement and Targets cards with no data. | USer has 0 posting activity. | 1.Open insights page. | Avg Engagement' should show 'post more to unlock' and 'Targets·30D' should show 'add engagement targets' until enough data exists. | As expected | PASS
TC_34 | Insights—Pillar Balance Accuracy | Verify the Pillar Balance stat reflects actual pillar usage. | User has published posts but not all pillars. | 1. Open the Insights page. 2. Compare Pillar Balance to actual pillars used in posts. | The number of count should actually matches with actual post pillars. | As expected | PASS
TC_35 | Insights — Target Audience Sync with Strategy | Insights — Target Audience Sync with Strategy | User has a defined content strategy. | 1. Open Insights → Audience & Intent section. 2. Compare to the Strategy page's Target Audience text. | Both should show identical audience text with no mismatch. | As expected | PASS
TC_36 | Engage — Suggested People List | Verify the Engage page suggests people based on content pillars. | User has a defined content pillars. | 1. Open Grow-Engage page. | A 'Suggested for you' list of people should display, relevant to the user's content pillars, refreshed within the last 24 hours. | As expected | PASS
TC_37 | Engage — Keyword and Location Search | Verify searching for people by keyword and location. | User is on Engage page. | 1. Enter a keyword (e.g. 'Software tester'). 2. Optionally set a location. 3. Search. | Results should filter to relevant profiles matching the keyword and location. | As expected | PASS
TC_38 | Engage — Add to Favourite | Verify adding a suggested profile to favourites. | User is viewing the suggested people list. | 1. Click 'Add to Favourite' on a profile. | Profile should be marked as favourited and shown in favourites section. | As expected | PASS
TC_39 | Strategy — View Content Pillars | Verify the Strategy page displays the users content pillars correctly. | User has completed onboarding setup. | 1. Open the Strategy page. | Pillars, Themes, Rules, and Plan stat cards should display accurately, along with the pillar donut chart and list. | As expected | PASS
TC_40 | Strategy — Edit Strategy | Verify editing the content strategy updates pillars and audience. | User is on Strategy page. | 1. Click 'Edit Strategy'. 2. Modify a pillar or audience detail. 3. Save. | Changes should save and reflect immediately on the Strategy page. | As expected | PASS
TC_41 | Edit Strategy — Update a Pillar | Verify updating a content pillar saves correctly. | User is on Strategy page. | 1. Click 'Edit Strategy'. 2. Change one pillar name/topic. 3. Save. | Updated pillar should reflect immediately in both the list and the donut chart on the Strategy page. | As expected | PASS
TC_42 | Stat Cards Accuracy | Verify Pillars, Themes, Rules, and Plan stat cards show correct values. | User is on Strategy page. | 1. Open Strategy page. 2. Compare each card's number to the actual account setup | Cards should show accurate counts | As expected | PASS
TC_43 | Voice DNA Section Visibility | Verify 'Your Voice DNA' section displays below the pillars. | User is on Strategy page. | 1. Scroll down on the Strategy page. | Section should be visible with voice related data captured from onboarding samples. | As expected | PASS
TC_44 | Feedback — Submit with Rating Only | Verify feedback can be submitted with just a star rating. | User clicks 'Share feedback'. | 1. Select a star rating. 2. Leave the text box empty. 3. Click 'Send feedback'. | Feedback should submit successfully since the text field is optional, and the modal should close with a confirmation. | As expected | PASS
TC_45 | Feedback — Send Button Disabled Without Rating | Verify the Send feedback button stays disabled with no rating. | User has the feedback modal open. | 1. Leave the star rating unselected. 2. Observe the 'Send feedback' button. | Button should remain disabled out until a rating is selected. | As expected | PASS
TC_46 | Mobile Responsivenes Sweep | Verify layout holds at mobile viewport width across all pages. | Consistly.ai opened on a mobile device or emulator. | 1. Visit Home, Signup, Login, Onboarding and Dashboard pages. | All page elements should be properly aligned with no overlapping. | As expected | PASS
TC_47 | Performance test on mobile | Verify the overall performance on mobile devices. | Open pageSpeed Insights | 1. Enter URL of the website on pageSpeed Insights. 2. Check for mobile performance. | Overall performance should be above 90. | Performance Result is 60. | Fail
TC_48 | Performance test on desktop. | Verify the overall performance on desktop devices. | Open pageSpeed Insights | 1. Enter URL of the website on pageSpeed Insights. 2. Check desktop performance. | Overall performance should be above 90. | As expected | PASS

## Bug Report
Tester Name: | Muhammad Ali
Website Name: | Consistly.ai
Bug ID | Located | Summary | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity | Issue type | Platform | Evidence
Bug_01 | Engage | Profile picture shown in the side panel does not match the selected LinkedIn profiles identity. | 1. Go to Engage page. 2. Search 'Software Quality Assurance' + Pakistan location. 3. Click on 'Mohammad Saad Sajid - Principal Software QA Engineer' from the People list. 4. Observe the profile picture shown in the opened side panel. | The photo displayed should be the actual LinkedIn profile picture of the selected person. | Mismatched photo is shown that does not appear to belong to the named person | HIGH | HIGH | Data Fetching | Web | https://www.loom.com/share/5eca568096514a62b03eacc71aaf35a6
Bug_02 | Activity | Deleting a post directly on LinkedIn does not sync back, the post still counts in Activity/Insights stats. | 1. Publish a post via Consistly to LinkedIn. 2. Go to LinkedIn directly and delete that post. 3. Return to Consistly's Activity page and check the post count/list. | The deleted post should be removed from Activity and post count. | Post count still shows even though it is deleted directly from LinkedIn. | High | Low | Data Loading | Web | https://www.loom.com/i/f672acd56dd64c26adfe0422f1473dda
Bug_03 | Signup-Email Verification OTP | After multiple wrong OTP attempts, entering the correct OTP still fails with a 'failed attempt' error even after requesting a new code via Resend. | 1. Start sign up with a valid email. 2. Receive the OTP code via email. 3. Enter the OTP incorrectly 4-5 times in a row. 4. Enter the correct OTP. 5. Observe the result process does not proceed and shows a 'failed attempt' error. 6. Click 'Resend code' to request a new OTP. 7. Enter the newly received (correct) OTP. 8. Observe the result again. | Entering the correct OTP should verify successfully and let the user proceed to the next signup step. If the account gets locked after too many wrong attempts, the system should clearly state the lockout duration | Correct OTP is rejected with a generic 'failed attempt' error, even after entering the right code | High | HIGH | Authentication | Web | https://www.loom.com/i/3472b4de0c6640c68dcdbe1b50e5eb76
Bug_04 | Dashboard-Home page tutorial | Clicking on media icon showing on right side of the page to see tutorial, video unavailable error shown. | 1.Go to homepage. 2.Click on blue media icon on the top right corner. 3.Observe the result, it shows 'video unavailable' error. | Clicking on should shows a video tutorial, how to use homepage and tells about the features. | It shows an error, no video is available. | High | Low | Data Loading | Web | https://www.loom.com/share/bcf5b49ae7c1477eadac29cb41c33c67
Bug_05 | Weekly ideas- save idea button | After writing something in box and click on save idea button nothing happened, just showing generating idea. | 1.Go to ideas page. 2.Write something in the box. 3.Click on save ideas. 4.Observe the response. | It should shows in saved ideas folder, so that we can pick that idea sometime. | No option available of saved ideas on the page, nothing happened. | High | HIGH | Functional | Web | https://www.loom.com/share/e04fc98efcee43caa00b9806cbadf7ff
Bug_06 | Carousels | Download PDF' button takes excessively long to download the carousel PDF. | 1. Create a carousel (using Standard/Pro template). 2. Once carousel is generated, click 'Download PDF'. 3. Observe the time taken for the download to start. | PDF should generate and start downloading within a reasonable time. | Button takes a long time to respond no clear loading progress indicator was visible, leaving it unclear whether the action is processing or stuck. | High | Low | Performance | Web | https://www.loom.com/share/414b05ac430d46c8b9ddea1f27590b62
Bug_07 | Mobile Responsiveness